## Sheet1
| Start Date | Duration
Dynamic Meshes on USDZ | 2022-02-02 | 15
Automatic Pipeline Python | 2022-02-17 | 42
GUI | 2022-03-31 | 14
Write Up | 2022-04-14 | 14
Completion | 2022-04-28